Assignment 2: Development Plan & Methodology Selection

Group: CSE-2501M

Name: Koshikov Alimzhan

| Course | Software Development Case Study |
| --- | --- |
| Week | Week 3 - Software Development Methodologies |
| Team Size | Maximum 2 students (same group) |
| Deliverables | Selected methodology with justification and project milestones. Risks. |

Task Description:

- Methodology Selection and Justification (25 points):

| Criterion | Waterfall | Scrum | Kanban | SAFe / Hybrid | Your score → (0 Not fit / 1 Partial / 2 Fits) |
| --- | --- | --- | --- | --- | --- |
| Requirements clarity at the start | 0 | 2 | 1 | 2 | Write your score here |
| Team size | 1 | 1 | 2 | 0 | Write your score here |
| Stakeholder involvement | 0 | 2 | 1 | 1 | Write your score here |
| Tolerance for change | 0 | 2 | 2 | 2 | Write your score here |
| Timeline flexibility | 0 | 2 | 2 | 1 | Write your score here |
| Delivery model | 0 | 2 | 1 | 2 | Write your score here |
| Best suited when… | 0 | 2 | 1 | 1 | Write your score here |
| TOTAL (max 14) | 1 / 14 | 13 / 14 | 10 / 14 | 9 / 14 | Highest score = your justified choice |

Of course, Scrum also has some disadvantages. It adds some extra process, like sprint planning and backlog updates, which takes time. It is also not always perfect for research work, because some results, especially in ML experiments, are hard to predict in short sprint cycles. Even so, Scrum is still the most suitable choice here because the project needs structure, clear milestones, and gradual progress.

| Annotated Example — Methodology Justification |  |
| --- | --- |
| STRONG Scrum is the best choice for this project because it fits the way the system will actually be developed. The requirements are not fully fixed from the beginning, since some parts may still change during implementation, such as the analyzer, student model, pedagogical policy, feedback engine, and ML component. Because of this, Scrum is more suitable than Waterfall. Advantages: - The main advantage of Scrum is its flexibility. It allows the project to adapt when implementation details change. This is important for my system because the core idea is already clear, but the exact technical decisions may still change during development. - Another advantage is step-by-step development. The project does not need to be built all at once, it makes the process more realistic, manageable, and less risky. - Scrum is also useful because it gives clear structure and progress tracking. Work can be divided into small iterations, which makes it easier to monitor what is done, what still needs improvement, and what should be prioritized next. | WEAK Of course, Scrum also has some disadvantages. - It adds some extra processes, like sprint planning and backlog updates, which takes time. - It is also not always perfect for research work, because some results, especially in ML experiments, are hard to predict in short sprint cycles. |

- Project Timeline & Milestones:

| Phase / Sprint | Dates | Main work | Output |
| --- | --- | --- | --- |
| Sprint 1 | 6 Apr 2026–12 Apr 2026 | Finalize requirements, refine architecture, confirm modules and data flow | Clear project scope and updated architecture |
| Sprint 2 | 13 Apr 2026–19 Apr 2026 | Implement baseline backend pipeline: analyzer, DTOs, session tracking, interaction logging, rule-based policy | Working backend prototype |
| Sprint 3 | 20 Apr 2026–26 Apr 2026 | Build frontend workflow, connect REST/WebSocket, show feedback in interface | End-to-end prototype |
| Sprint 4 | 27 Apr 2026–3 May 2026 | Improve feedback generation, integrate templates and external LLM phrasing with constraints | Usable pedagogical feedback layer |
| Sprint 5 | 4 May 2026–10 May 2026 | Prepare ML policy dataset, train preliminary classifier, expose prediction API, connect ML mode | ML-extended prototype |
| Sprint 6 | 11 May 2026–17 May 2026 | Run tests, measure latency and behavior, fix issues, finalize documentation | Final tested version and report |

The three required milestones are these:

Prototype Demo — 19 April 2026.
By this point, the system should already have a working backend pipeline with at least a rule-based policy and basic interaction logging.

Testing Milestone — 10 May 2026.
By this date, the frontend, backend, and optional ML service should already be integrated, and latency plus behavior testing should begin.

Final Submission — 17 May 2026.
By this point, the system should be documented, tested, and presented as a complete development result.

- Requirement Traceability:

| Req. ID (from A1) | Requirement Summary | Task(s) | Sprint / Phase | Responsible | Status |
| --- | --- | --- | --- | --- | --- |
| FR-01 | Monitor code changes in real time | Implement editor event capture, connect WebSocket updates, trigger analysis on edits | Sprint 3 | Alimzhan | Not started |
| FR-02 | Detect syntax, beginner, and simple logic errors | Implement analyzer module, define error categories, add heuristic checks | Sprint 2 | Alimzhan | Not started |
| FR-03 | Maintain a simple student model | Create student/session state structure, store repeated error counts and feedback history | Sprint 2 | Alimzhan | Not started |
| FR-04 | Generate adaptive feedback | Build feedback engine, define actions such as hint, highlight, question, or no feedback | Sprint 4 | Alimzhan | Not started |
| FR-05 | Avoid giving full solutions | Add pedagogical constraints, filter solution-like output, define safe prompt/response rules | Sprint 4 | Alimzhan | Not started |
| FR-06 | Respond almost instantly during coding | Optimize analysis flow, minimize heavy processing in critical path, monitor latency | Sprint 5–6 | Alimzhan | Not started |
| FR-07 | Log all interactions for future improvement | Design interaction log schema, save events, support dataset export for policy learning | Sprint 1–5 | Alimzhan | Not started |
| NFR-01 | Log all interactions for future improvement | Design interaction log schema, save events, support dataset export for policy learning | Sprint 1-5 | Alimzhan | Not started |
| NFR-02 | Usability: integrated into web-based IDE, simple feedback | Design clean frontend feedback panel, reduce clutter, keep messages short and understandable | Sprint 3–4 | Alimzhan | Not started |
| NFR-03 | Reliability: stable during coding sessions | Add exception handling, fallback behavior, test repeated session workflows | Sprint 6 | Alimzhan | Not started |
| NFR-04 | Scalability: support many students | Keep logic modular, avoid unnecessary heavy runtime processing, test concurrent usage assumptions | Sprint 5–6 | Alimzhan | Not started |
| NFR-05 | Security and privacy of interaction data | Store logs safely, anonymize student data, restrict sensitive output and access | Sprint 2 and Sprint 6 | Alimzhan | Not started |
| NFR-06 | Maintainability through modular architecture | Keep analyzer, policy, feedback, session, and UI layers separate | Sprint 1–2 | Alimzhan | Not started |
| NFR-07 | Ethical design: support learning, not cheating | Enforce no direct solution disclosure, align feedback style with educational purpose | Sprint 4-5 | Alimzhan | Not started |

- Risk Register & Dependency Map:

| # | Risk Description | Prob. (H/M/L) | Impact (H/M/L) | Priority (P1–P3) | Strategy (Avoid/Mitigate/ Accept/Transfer) | Mitigation Action | Owner & Deadline |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | ML policy model does not have enough authentic labeled data | M | H | P1 | Mitigate | Start with rule-based baseline, use weak supervision and log collection for first dataset | Dev Lead — Sprint 7 |
| 2 | Frontend, backend, and ML service integration becomes more complex than expected | M | H | P1 | Mitigate | Use clean API boundaries, keep ML as optional service, preserve rule-based fallback | Dev Lead — Sprint 6 |
| 3 | Academic deadlines leave insufficient time for full implementation and testing | M | H | P1 | Mitigate | Prioritize working prototype first, then refinement, then ML extension | Dev Lead — Ongoing |
| 4 | External LLM/API provider changes pricing or output behavior | M | M | P2 | Accept + Mitigate | Keep template-based feedback as fallback and isolate provider calls in one service layer | Dev Lead — Sprint 5 |

The main dependencies between tasks are straightforward. The system architecture must be clarified before coding begins. The analyzer and session model must be implemented before adaptive feedback can work. The frontend depends on stable backend endpoints and event flow. The ML policy depends on the interaction logging pipeline, because without logs there is no usable dataset. Testing depends on the integration of all previous parts. So the practical dependency chain is:

Requirements and architecture → backend analyzer and session logic → feedback engine → ML policy integration → frontend integration → testing and evaluation.

Conclusion

In conclusion, Scrum is the most suitable methodology for this project because it matches how the system will actually be developed. The requirements are partly clear, but some parts can still change, so an incremental approach is more practical than a strict one. At the same time, since the project is also connected to research, Design Science Research supports it well by treating the virtual mentor as an artifact that must be designed, built, and evaluated.

The development plan is also realistic because it starts with a simple rule-based version, then gradually adds real-time interaction, feedback generation, ML-based policy selection, and final evaluation. As a result, the project is expected to deliver not just a simple chatbot, but a structured virtual mentor system that can give real-time and personalized support to beginner programmers.